## Slide 1: WP4 HARMONIZING OPERATION AND MAINTENANCE METHODS
HCMR

## Slide 2
Based on the experience of infrastructure operators and relevant regional activities, this WP will:
- gather elements of best practice in conducting operations and maintaining coastal observatories,
- identify the successes in terms of systems autonomy and reliability,
- propose common procedures to be followed by all operators

## Slide 3
WORK PACKAGE: 4 |  |  |  | TITLE: HARMONIZING OPERATION AND MAINTENANCE METHODS |  | 
WORK PACKAGE LEADER : George Petihakis |  |  |  |  |  | 
TASKS |  | ACTIVITIES |  | Task leader (Organisation) | Initial end date (month) | Actions
N° task | Task | N° sub-task | Sub-task |  |  | 
4.1 | CALIBRATION |  |  | HZG | M1 – M42 | standardize and harmonize various facilities across European networks share existing calibration facilities within the network, thus significantly reducing costs exchange and transfer know-how within the network through a series of workshops, seminars and staff Exchange
 |  | 4.1.1 | Physical sensors T, S, DO, Currents, Sea-bed Pressure | OGS |  | 
 |  | 4.1.2 | Optical sensors Chl-a, Turbity, PAR | SMHI |  | 
 |  | 4.1.3 | Chemical sensors-Nutrients | HZG |  | 
4.2 | BIO FOULING PREVENTION |  |  | CNR | M1 – M42 | all different methods used across the network will be described with reference to the cost (implementation, maintenance) and adaptability (different sensors and areas) there will be sharing of best practices and methodologies across the network with the aim towards a common approach; new methods used by the community external to Jerico will be evaluated to identify and suggest possible future implementation.
 |  | 4.2.1 | Physical sensors | HCMR |  | 
 |  | 4.2.2 | Optical sensors Chl-a, Turbity, PAR | SYKE |  | 
 |  | 4.2.3 | Chemical sensors-Nutrients | CNR |  | 
4.3 | END TO END QUALITY ASSURANCE |  |  | HCMR | M1 – M42 | to describe best practices in all phases of the system (pre-deployment test, maintenance, calibration etc); to adopt common methodologies and protocols; move towards the harmonisation of equipment which will help in reducing maintenance and calibration costs. For this inter calibration tests and in-situ validation will be organised.
 |  | 4.3.1 | Fixed Platforms | PUERTOS |  | 
 |  | 4.3.2 | Ferry Box | NERC(NOCS) |  | 
 |  | 4.3.3 | Gliders | CSIC |  | 
 |  | 4.3.4 | Running costs | CEFAS |  | 

## Slide 4: Deliverables
D4.1) Report on existing facilities: Task 4.1 - Report on existing facilities with the capacity to handle pressure, temperature, salinity and dissolved oxygen calibrations amongst the active coastal observing networks [month 18]  Questionnaire
D4.2) Report on calibration best practices: Task 4.1 - Report on calibration best practices for the different sensors [month 36]  Workshop
D4.3) Report on biofouling prevention methods: Task 4.2 - Report on biofouling prevention methods [month 36]  Workshop + exercises
D4.4) Report on best practice in operation and maintenance: Task 4.1 - Report on best practice in conducting operations and maintaining of different systems [month 42]  Workshop
D4.5) Report on running costs: Task 4.3 - Report on running costs of observing systems [month 42]  Questionnaire

## Slide 5: Milestone: Constitution of a permanent WG for calibration activities
Who will be in that working group?
1 Representative from each calibration lab within JERICO +
What will be the responsibilities of the WG?
Monitoring of activities, proposal of actions, deviations etc
How the WG will interface with the task and sub-tasks ?
Through the task responsible and through workshops.
This WG will be established in month 30 and its operation will probably continue after the end of the project. This long term function is more important than interface with tasks/subtasks. It will actually use and consolidate the experience gained during the JERICO project

## Slide 6: Cont.. Harmonise workshops with WP3 - consider joint workshops with plenum and dedicated session
This is very important not only to reduce costs but most people will be involved in both WP3 and WP4 with the exception of IBWPAN (WP3) and IH(WP4)
Proposed times:
  M6 to discuss current practices
  M18
  M30
  M42

## Slide 7: Task 4.1 CALIBRATION
Works have been done by other EU projects (WP2 ESONET + …)
Outcomes of WP2 + relevant materials from other projects will be collected by the WG.
The work of EuroSITES (plus the OceanSITES – global program with a lot of experience e.g. TAO array) is more relevant. Indeed the suite of sensors in JERICO are closer to the sets used in EuroSITES (& of course FerryBox and EGO)
What will be the starting point of the Task?
Recording of current practices of partners into a report which will be circulated into the consortium.
Recording of practices outside the consortium into a report which will be circulated into the consortium
Will other experiences been shared and how?
Through the report , the workshops, the website +???

## Slide 8: Task 4.2 BIO FOULING PREVENTION
Works have been done by other EU projects (WP2 ESONET + …)
Outcomes of WP2 + relevant materials from other projects will be collected by the WG
What will be the starting point of the Task?
Recording of current practices of partners into a report which will be circulated into the consortium.
Recording of practices outside the consortium into a report which will be circulated into the consortium
Will other experiences been shared and how?
Through the report , the workshops, the website +???

## Slide 9: Task 4.3 END TO END QUALITY ASSURANCE
How this task will be interfaced with WP10.3 (EMERGING TECHNOLOGY - PROFILING TECHNOLOGY, INTER-COMPARISON WITH MATURE TECHNOLOGY)?
Outcomes from WP4 will demonstrate possible needs for new technology