## Slide 1: WP1

## Slide 2: WP1
Scientific coordination
TASK 1.1 : SET UP THE SCENE AND IMPLEMENTATION PLAN( M1-M24)
  Roadmap for the project (WP by WP)
  Coordination of WP results
  Share the experience with other projects
TASK 1.2: JERICO LABEL (M1-M12)
  defining the JERICO label for coastal observatories and technology

## Slide 3: WP1
TASK 1.3: FCT - FORUM FOR COASTAL TECHNOLOGY (M6-48)
  implementing a forum to better encourage communication and collaboration between public scientists, managers, and private companies
  animating a scientific secretariat aimed at organizing the meetings and working groups
TASK 1.4: DEFINITION STRATEGY AND INTERFACES WITH THE MONITORING OF MARINEBIODIVERSITY (M12-42)
  NIOZ task Leader
  Carlo Heip and Hermann Hummel

## Slide 4: WP1
TASK 1.5: ROADMAP FOR THE FUTURE (M24-48)
  Proposal for the « after Jerico »
  Recommendations for the European structures
  How to built a real Network
TASK1.6: USER MODALITY ACCESS FOR THE TRANS NATIONAL ACTIVITIES
  To be discussed in WP8 presentation

## Slide 5: WP2

## Slide 6: WP3
All tasks | Please Identify the Task and Sub tasks leaders (name and organization) | HZG | List to be sent to the coordinator
 | and a schedule of the main actions of each task/subtasks |  | Scheduling to be discussed in march
Deliverable 3.4 | Report on new sensor development must take into account new parameters to | HZG | Provide a more detailed description
 | measure and new methodologies. We need to take into account what is yet done |  | 
 | in terms of inter-operability, plug and play. What will be the interface with WP10 |  | 
Workshops | Harmonise workshops with WP4 - consider joint workshops with plenum and dedicated session | HZG + HCMR | Planning to be discussed in March
3.1.3 & 3.3.1 | How will you manage and what are the interfaces with WP2 ? | HZG + IMR | Provide a more detailed description

## Slide 7: WP4

## Slide 8: WP5

## Slide 9: WP6

## Slide 10: WP9
Task number | Question | To who | Action
all | Please detail the work plan and the agenda of the WP9? | CMCC | Work plan and agenda
all | What will be the output of the WP9 ? Recommendation, strategic plan ? | CMCC | New WP9 description of work

## Slide 11: WP10

## Slide 12: WP7
TASK 1: access to data
  13 partners
  Access from Jerico portal
  2 years of data
  Compliant with Seadatanet and Myocean
  Open to users
      Identification rules
      Communication to be defined

## Slide 13: WP7
3 Targeted Operation Phase (TOP) are proposed to offer access to data and value-added products, including:
- Multi parameters maps on a monthly basis, provided by a set of coastal observatories (moored buoys, floats) – CEFAS, BL
- Data and demonstrative products on a monthly basis, collected from sensors on board fishing vessels – Ifremer, CNR
- Data from buoys and collocated Ferry Box line, respectively in the south Aegean Sea and in the Kattegat – NIVA, SMHI
1 year of data

## Slide 14: WP7
Task number | Question | To who | Action
TOP 1 | EMECO. Better definition of the task, how to realize the EMECO extension to | CEFAS | To be discussed in Brussels
 | other regional seas? On what basis (i.e. data accessible via the jerico web (WP7)? |  | 
TOP 2 | Objectives of the TOP? Approach to 2D/3D? Cross calibration? | Ifremer - CNR | To be discussed in Brussels
TOP 3 | Objectives of the TOP? Approach to 2D/3D? Cross calibration? | NIVA - HCMR | To be discussed in Brussels

## Slide 15: WP7
WE NEED TO BE VERY STRICT ON THE ANALYTICAL COST ACCOUNTING BECAUSE OF THE AUDIT BY THE EC
  PERSONNEL COSTS
  OPERATIONNAL COSTS
  SPARE PARTS,
  NO INVESTMENTS
  DURING 1(TOP), 2(DATA), 4 TNA years

## Slide 16: WP8
Question | To who | Action
Prepare a template for all the partners involved in the WP8 : | CNR | Discussion in Brussels
# parameters characteristics, geolocalization, time scale … |  | TEMPLATES
# definition of metadata |  | 
# dedicated web server |  | 
# owner rules |  | 
Administrative rules for the partners: what they have to do for the financial | CNR | Discussion in Brussels
aspects (analytical cost accounting), how they have to justify, … |  | TEMPLATES