## Slide 1
This task manages the Trans National Access to selected installations of the JERICO network.
SubTask 1.6.1: Preparation of the call – peer review
- Setting the “Selection Panel”.
- Drafting the call.
- Drafting the guidelines for evaluation.
- Meetings of the Panel.
SubTask 1.6.2 : Information and reporting activities
- Drafting the specifications of the web site (call section),
managing its construction and implementation.
- Managing the calls (call opening, proposals reception and
transmission to the targeted providers for pre-screening
technical review).
- Access reporting and information.
JERICO WP1
T1.6 : User modality Access for the Trans National Activities

## Slide 2
JERICO WP1 – T1.6
Roadmap and planning for WP8 – 1st year
Month | Action
[1] – May 2011 | Setting the Selection Panel (SP)
[6] – Oct 2011 | Drafting the TNA call and the guidelines for evaluation
[7] – Nov 2011 | 1st SP meeting: validation of call and guidelines validation, and information to post on the website, schedule of call openings, deadlines and access calendar
[8] – Dec 2011 | TNA webpages ready to publish call and related material Call opening: 1st call for TNA proposals
[10] – Feb 2012 | Technical pre-screening by the targeted providers of submitted projects
[11] – Mar 2012 | 2nd SP meeting: selection of the projects, publication of the assessment report and the calendar of planned access
[11] – Mar 2012 | MS6 – Infrastructure available for users

## Slide 3
Month | Action
[13 to 23] May 2012 – Mar 2013 | Trans National Access to JERICO network: user groups and providers implement the projects selected after the 1st call
[20] – Dec 2012 | Call opening: 2nd call for TNA proposals
[22] – Feb 2013 | Technical pre-screening by the targeted providers of submitted projects
[24] – Apr 2013 | First report of the access activity
JERICO WP1 – T1.6
Roadmap and planning for WP8 – 2nd year

## Slide 4
JERICO WP1 – T1.6
Roadmap and planning for WP8 – 3nd year
Month | Action
[26] – June 2013 | 3rd SP meeting: selection of the projects from the 2nd call, publication of the assessment report and the calendar of access planned for the last period
[29 to 39] Sept 2013 – Jul 2014 | Trans National Access to JERICO network: user groups and providers implement the projects selected after the 2nd call
[42] – Oct 2014 | Second report of the access activity
[47] – Mar 2015 | MS13 – User reports of TNA activities plus TNA recommendations for a strategic implementation plan of the infrastructure to cover all the European coast line and waters

## Slide 5
T1.6 : Third year
Sub-Task | Activity | Description | Delivery date
1.6.1 Preparation of the call – peer review | 3nd Meeting of the “Selection Panel”. | Selection of the projects submitted to the second open call. Publication on the web page of the assessment report and the calendar of user groups to be hosted in the JERICO facilities. | 26
1.6.2 Information and reporting activities | Trans National Access to the JERICO network. | User groups and the providers implement the selected projects and related access to the concerned installations (establishment of a protocol between the provider and the user to state all the access details when necessary). For each facility allocated a reporting mechanism will be introduced at the end of the testing period quantifying the scientific and technological outcomes being achieved. | 29 to 39
 | D1.10 - Second report of the access activity | Release on the JERICO web site of the second annual report of the access activity. It will describe the selected open projects under the TNA programme and their scientific and technological outcomes. | 42
 | MS13 – User reports of activities plus Contribution to D1.11 – Final report including a roadmap for the next decade | User reports of TNA activities and TNA recommendations will be produced for a strategic implementation plan of the infrastructure to cover all the European coast line and waters. | 47